## event planning checklist
Name: Easter
Location: Your Church
Date(s): April 1, 2018
Partner(s): Multiple
Primary Contact (PC): Name
X or N/A | 3 Months Prior- 01/01/18 | ASSIGNED TO | NOTES
X | Confirm Date(s)- April 1, 2018 | Primary Contact
Confirm Partner(s) & Venue Location
Begin Mother's Day/post-Easter sermon series planning
| Formulate Easter Marketing Budget | Executive Pastor
Gameplan your team's resource management strategy
| Brainstorm event components (i.e. photo booths, giveaways, memories, etc.) | Lead Pastor
Fill out & Distribute Event Campaign Sheet
X or N/A | 2 Months Prior- 02/01/18
status check: my team's resource management (How much time, energy, budget are we actually conserving?)
Include the whole family in marketing strategy (i.e. dad, mom, kids, extended family, etc.)
| Develop Easter sermon series for both adults & kids | Lead Pastor/Kids Pastor/PC
Purchase Supplies
status check: marketing/event budget (Am I on target? Do I need to adjust?)
Develop/distribute Easter invite cards
Update event Campaign Sheet & redistribute if needed
Direct Mail (protip: consider Outreach Inc.for help on this.)
X or N/A | 1 Month Prior- 03/01/18
Develop Easter follow up strategy & sequence (free resource: download "Perfect Follow-Up Plan" in ReThinkng Easter Module)
Design/update Connect Card (free resource: "Connect Card Tips" in ReThinking Easter Module)
Recruit volunteers to assist with post-Easter details (i.e. data entry, thank you cards, etc.)
status check: my team's resource management (How much time, energy, budget are we actually conserving?)
Develop communication deliverables (i.e. web elements, print deliverables, bulletins, etc.)
Update Event Campaign Sheet & redistribute if needed
X or N/A | 2 Weeks Prior- 03/18/18
Develop/send out Press Release (if applicable)
Connect with hospitality teams
Consider adding in "pre-registration for kids" on website
Finalize remaining communication plans (i.e. web, socials, prints, ads, etc.)
X or N/A | 1 Week Prior- 03/25/18
Begin Facebook Ads Strategy
status check: my team's resource management (How much time, energy, budget are we actually conserving?)
status check: print deliverables. (i.e. direct mail in hand, door hangers, etc.)
X or N/A | 1 Week After- 04/08/18
Continue executing follow up strategy
share Easter "wins"/"testimonies" with entire team!
X or N/A | 2 Weeks After- 04/15/18
Continue executing follow up strategy
X or N/A | 1 Month After- 05/01/18
Continue executing follow up strategy (keeping in mind Mother's Day is almost here)
Note on B11: this can turn into a separate checklist and campaign sheet for Mother's Day too (and all future events).
Note on B13: plan ahead to make sure energy and time are still available for the weeks following Easter!
Note on B20: (pro tip: consider making Easter a kick off for your new series to gain momentum)
Note on B21: purchase any budgeted items that are non-perishable early on so they aren't a last minute concern.
Note on B25: this approach can help layer your marketing for better long-term connectivity with guests.
Note on B32: finalize these now so that they aren't taking bandwidth the week of Easter.
Note on B38: communicate the win, need, etc. with anyone dealing with guests.